Joe Perks

Epics & User Stories

MVP Development Handoff  ·  March 2026  ·  v2.0 (Gap Audit Complete)

| Document | Value |
| --- | --- |
| Document version | v2.0 — Gap audit complete |
| Total epics | 8 |
| Total user stories | 39 (34 original + 5 new from gap audit) |
| Total story points | 217 |
| Estimated sprints | 5 (10 weeks) |
| Sprint cadence | 2 weeks per sprint |
| Target launch | MVP live — Q2 2026 |
| Gap audit status | All 7 missing items addressed. All 9 partial items tightened. |
| Reference docs | PRD v1.0 · DB Schema Reference v1.0 |
| New stories (v2.0) | US-01-08 legal pages, US-01-09 rate limiting, US-01-10 cart cleanup + Posthog, US-04-05 shipping guard |
| Tightened stories (v2.0) | US-01-01 US-01-02 US-01-07 US-02-01 US-03-01 US-04-01 US-04-02 US-04-03 US-05-01 |

# How to Use This Document

This document defines all work required to deliver the Joe Perks MVP. It is structured for direct import into Jira, Linear, GitHub Projects, or any agile tracking tool.

Document structure Section 1: Epic summary table — 8 epics with updated point totals and sprint targets Section 2: Sprint plan — 5 sprints with all 39 stories, points, and dependencies mapped Section 3: Story cards — full detail for every story including acceptance criteria, tech notes, and definition of done Gap audit additions are marked in the story ID sequence: US-01-08, US-01-09, US-01-10, US-04-05 are new. Tightened stories are marked with updated ACs. Each story card can be imported as a single ticket in Jira, Linear, or GitHub Projects

## Story Card Anatomy

| Field | Description |
| --- | --- |
| Story ID | Unique identifier in format US-[epic]-[sequence] e.g. US-01-01. Use as ticket ID. |
| Epic | Parent epic this story belongs to |
| Sprint | Recommended sprint. Adjust based on team capacity. |
| Points | Story point estimate (Fibonacci: 1, 2, 3, 5, 8, 13). Reflects complexity not time. |
| Priority | High = MVP blocker · Medium = important but can slip a sprint · Low = nice to have |
| Status | Todo / In Progress / Done / Blocked — update as work progresses |
| Dependencies | Story IDs that must be complete before this story begins |
| Acceptance Criteria | Numbered conditions that must ALL pass for the story to be considered done |
| Technical Notes | Implementation hints, patterns, and references to design documents |
| Definition of Done | Minimum verifiable outputs to close the story — not full test suite |

## Priority Definitions

| Priority | Definition | Sprint Impact |
| --- | --- | --- |
| High | MVP blocker — platform cannot take its first order without this | Never defer beyond planned sprint |
| Medium | Important — creates meaningful gaps if missing but not launch-blocking | Can slip one sprint maximum |
| Low | Enhancement — adds value but system works without it | Can defer to Phase 2 if sprint overloads |

# Section 1 — Epic Summary

EP-01 Foundation & Infrastructure · 42 pts · Sprint 1

Monorepo scaffold, database, auth, email, environment setup, legal placeholder pages, rate limiting infrastructure, and Sentry. Zero user-visible features — pure infrastructure. Everything else depends on this. Updated to include 3 new stories from gap audit (US-01-08, US-01-09, US-01-10).

EP-02 Roaster Onboarding & Products · 42 pts · Sprint 2

Roaster application form, admin approval queue, Stripe Connect onboarding, product/variant catalog setup with live margin preview, and shipping rate configuration with availability guard.

EP-03 Org Onboarding & Approval Chain · 38 pts · Sprint 2–3

Org application form, platform admin review, roaster approval magic link flow, Stripe Connect for org payouts, campaign setup.

EP-04 Buyer Storefront & Cart · 38 pts · Sprint 3

Public org-slug storefront, product grid, Zustand cart with mobile bottom sheet, three-step checkout with Stripe Elements and rate limiting, analytics instrumentation. Updated to include US-04-05 Posthog story from gap audit.

EP-05 Order Processing & Fulfillment · 40 pts · Sprint 4

Stripe webhook handler, order creation with Buyer upsert, magic link fulfillment email, roaster marks shipped, buyer tracking notification.

EP-06 Payments, Payouts & Audit · 36 pts · Sprint 4–5

Payout job with 7-day hold, roaster and org Stripe transfers, debt ledger, order event log, and chargeback webhook handling.

EP-07 Admin Dashboard & Monitoring · 28 pts · Sprint 5

Platform admin panel: approval queues, order list, SLA flags, basic dispute visibility, PlatformSettings editor.

EP-08 Transactional Email System · 22 pts · Sprint 3–4

All transactional emails: order confirm, shipped, delivered, impact message, SLA nudges, approval notifications using React Email + Resend.

| Epic ID | Title | Sprint | Points | Stories |
| --- | --- | --- | --- | --- |
| EP-01 | Foundation & Infrastructure | Sprint 1 | 42 pts | 10 stories |
| EP-02 | Roaster Onboarding & Products | Sprint 2 | 42 pts | 6 stories |
| EP-03 | Org Onboarding & Approval Chain | Sprint 2–3 | 38 pts | 4 stories |
| EP-04 | Buyer Storefront & Cart | Sprint 3 | 38 pts | 5 stories |
| EP-05 | Order Processing & Fulfillment | Sprint 4 | 40 pts | 3 stories |
| EP-06 | Payments, Payouts & Audit | Sprint 4–5 | 36 pts | 3 stories |
| EP-07 | Admin Dashboard & Monitoring | Sprint 5 | 28 pts | 4 stories |
| EP-08 | Transactional Email System | Sprint 3–4 | 22 pts | 6 stories |

# Section 2 — Sprint Plan

Sprint planning notes Each sprint is 2 weeks. Story points use Fibonacci scale: 1, 2, 3, 5, 8, 13. Recommended team: 2 full-stack developers + 1 part-time designer for Sprint 3–4 storefront work. Sprint 1 is pure infrastructure — no user-visible features. Resist the urge to skip or parallelize. Dependencies are strict: do not start a story until all listed dependencies are Done. Buffer: 10–15% of sprint capacity reserved for bug fixes, PR review, and unexpected complexity.

Sprint 1 Weeks 1–2 · 41 points · 10 stories

Foundation — infrastructure, schema, auth, email, Stripe webhook, rate limiting, legal pages, analytics scaffold

| Story ID | Title | Epic | Pts | Priority | Dependencies |
| --- | --- | --- | --- | --- | --- |
| US-01-01 | Turborepo monorepo scaffold with four apps, shared p... | EP-01 | 8 | High | — |
| US-01-02 | Complete Prisma schema with first migration against ... | EP-01 | 5 | High | US-01-01 |
| US-01-03 | Clerk authentication configured for roaster and org ... | EP-01 | 5 | High | US-01-01 |
| US-01-04 | Resend + React Email infrastructure with base templates | EP-01 | 5 | High | US-01-02 |
| US-01-05 | Stripe keys, webhook endpoint, and idempotency handler | EP-01 | 5 | High | US-01-02 |
| US-01-06 | Inngest configured with sla-check and payout-release... | EP-01 | 3 | Medium | US-01-01 |
| US-01-07 | Sentry error monitoring on all four apps | EP-01 | 3 | Medium | US-01-01 |
| US-01-08 | Legal placeholder pages: /terms/roaster, /terms/org,... | EP-01 | 2 | High | US-01-01 |
| US-01-09 | Rate limiting infrastructure via Upstash Redis on ch... | EP-01 | 3 | High | US-01-01 |
| US-01-10 | Cart cleanup Inngest stub job and Posthog analytics ... | EP-01 | 2 | Medium | US-01-06, US-01-01 |

Sprint 2 Weeks 3–4 · 44 points · 8 stories

Roaster onboarding — application form (with rate limiting), admin approval, Stripe Connect, products, shipping

| Story ID | Title | Epic | Pts | Priority | Dependencies |
| --- | --- | --- | --- | --- | --- |
| US-02-01 | Roaster application form (5 steps) on main site | EP-02 | 8 | High | US-01-02, US-01-04 |
| US-02-02 | Admin approval queue for roaster applications | EP-02 | 5 | High | US-02-01, US-01-03 |
| US-02-03 | Stripe Connect Express onboarding for roasters | EP-02 | 5 | High | US-02-02 |
| US-02-04 | Product and variant creation with wholesale/retail p... | EP-02 | 8 | High | US-02-03 |
| US-02-05 | Roaster shipping rate configuration | EP-02 | 5 | High | US-02-04 |
| US-02-06 | Slug reservation blocklist validation | EP-02 | 3 | Medium | US-01-02 |
| US-03-01 | Org application form (5 steps) on main site | EP-03 | 8 | High | US-01-02, US-01-04, US-02-06 |
| US-08-06 | Application received and approval/rejection notifica... | EP-08 | 2 | High | US-01-04 |

Sprint 3 Weeks 5–6 · 46 points · 9 stories

Org onboarding + buyer storefront — approval chain, campaign, cart with mobile UX, checkout, shipping guard, legal links

| Story ID | Title | Epic | Pts | Priority | Dependencies |
| --- | --- | --- | --- | --- | --- |
| US-03-02 | Admin org approval queue with routing to roaster review | EP-03 | 5 | High | US-03-01, US-02-02 |
| US-03-03 | Roaster magic link approval/decline of org | EP-03 | 5 | High | US-03-02, US-01-04 |
| US-03-04 | Org Stripe Connect onboarding and campaign creation | EP-03 | 5 | High | US-03-03, US-02-03 |
| US-04-01 | Public org storefront at joeperks.com/[slug] | EP-04 | 8 | High | US-03-04 |
| US-04-02 | Zustand cart with add, remove, quantity update, and ... | EP-04 | 5 | High | US-04-01 |
| US-04-03 | Three-step checkout: cart review, shipping details, ... | EP-04 | 8 | High | US-04-02, US-01-05 |
| US-04-04 | Order confirmation page with payment status polling | EP-04 | 5 | High | US-04-03 |
| US-08-01 | Order confirmation email to buyer | EP-08 | 3 | High | US-01-04, US-05-01 |
| US-04-05 | Shipping rate availability guard on storefront and c... | EP-04 | 2 | Low | US-02-05, US-04-01 |

Sprint 4 Weeks 7–8 · 46 points · 9 stories

Order processing, fulfillment, payouts — full transaction flow with Buyer upsert and PII-safe logging

| Story ID | Title | Epic | Pts | Priority | Dependencies |
| --- | --- | --- | --- | --- | --- |
| US-05-01 | payment_intent.succeeded webhook creates order and s... | EP-05 | 8 | High | US-01-05, US-04-03, US-01-04 |
| US-05-02 | Roaster magic link fulfillment page: view order and ... | EP-05 | 8 | High | US-05-01 |
| US-05-03 | Delivery confirmation and payout eligibility calcula... | EP-05 | 5 | High | US-05-02 |
| US-06-01 | Inngest daily payout job: find eligible orders and c... | EP-06 | 8 | High | US-05-03, US-01-06 |
| US-06-03 | Order event log append-only writes and query API | EP-06 | 5 | High | US-01-02 |
| US-08-02 | Roaster magic link fulfillment notification email | EP-08 | 3 | High | US-01-04, US-05-01 |
| US-08-03 | Shipped notification email to buyer with tracking | EP-08 | 3 | High | US-01-04, US-05-02 |
| US-08-04 | Delivery confirmation + impact email to buyer | EP-08 | 3 | High | US-01-04, US-05-03 |
| US-08-05 | SLA warning and breach notification emails | EP-08 | 3 | Medium | US-01-04, US-01-06, US-05-01 |

Sprint 5 Weeks 9–10 · 26 points · 5 stories

Admin dashboard, chargebacks, platform settings, QA, launch readiness checklist

| Story ID | Title | Epic | Pts | Priority | Dependencies |
| --- | --- | --- | --- | --- | --- |
| US-06-02 | Chargeback webhook handler with fault attribution an... | EP-06 | 8 | High | US-06-01, US-01-05 |
| US-07-01 | Admin order list with SLA flag indicators | EP-07 | 5 | High | US-05-01, US-01-03 |
| US-07-02 | PlatformSettings editor in admin | EP-07 | 5 | Medium | US-01-02, US-01-03 |
| US-07-03 | Basic metrics dashboard for admin | EP-07 | 5 | Medium | US-05-01, US-07-01 |
| US-07-04 | Admin can manage roaster and org accounts: suspend, ... | EP-07 | 3 | Low | US-07-01 |

## Dependency Map

Stories with the most downstream dependents — resolve blockers here first:

| Story ID | Title | Blocked by | Blocks (count) |
| --- | --- | --- | --- |
| US-01-01 | Turborepo scaffold + .env docs | — | All other stories (35+) |
| US-01-02 | Prisma schema + migration | US-01-01 | 26 stories |
| US-01-03 | Clerk auth setup | US-01-01 | 8 stories |
| US-01-04 | Email infrastructure | US-01-02 | 13 stories |
| US-01-05 | Stripe webhook + idempotency | US-01-02 | 6 stories |
| US-01-09 | Rate limiting (Upstash) | US-01-01 | US-02-01, US-03-01, US-04-03 |
| US-02-03 | Roaster Stripe Connect | US-02-02 | 5 stories |
| US-03-04 | Org Stripe + campaign creation | US-03-03 | 4 stories |
| US-05-01 | Webhook → order + magic link | US-01-05, US-04-03 | 6 stories |
| US-01-08 | Legal placeholder pages | US-01-01 | US-02-01, US-03-01 (terms links) |

# Section 3 — User Story Cards

Each card below represents one ticket. Import directly into your project management tool. All acceptance criteria must pass before a story is considered Done.

Definition of Done — applies to ALL stories Code reviewed and approved by at least one other developer All acceptance criteria manually verified by the implementing developer Unit tests written for any business logic (split calculations, validation functions, order number generation) No TypeScript errors (strict mode) Deployed to staging environment and smoke-tested Relevant documentation updated (README, API docs if applicable)

EP-01 · Foundation & Infrastructure 42 story points · 10 stories · Sprint 1

Monorepo scaffold, database, auth, email, environment setup, legal placeholder pages, rate limiting infrastructure, and Sentry. Zero user-visible features — pure infrastructure. Everything else depends on this. Updated to include 3 new stories from gap audit (US-01-08, US-01-09, US-01-10).

US-01-01 Turborepo monorepo scaffold with four apps, shared packages, and .env documentation

| Points | Priority | Status | Epic | Sprint |
| --- | --- | --- | --- | --- |
| 8 pts | High | Todo | EP-01 Infrastructure | Sprint 1 |

As a developer, I want to a working Turborepo monorepo with apps/web, apps/roaster, apps/org, apps/admin, and packages/db, packages/ui, packages/stripe, packages/email, packages/types so that all four apps can share the database schema, UI components, and business logic without duplication

Acceptance Criteria

| # | Acceptance Criteria |
| --- | --- |
| AC1 | Running `pnpm dev` from root starts all four Next.js apps simultaneously on different ports (3000, 3001, 3002, 3003) |
| AC2 | packages/db exports a Prisma client importable by all apps via `@joe-perks/db` |
| AC3 | packages/ui exports a base Button, Card, and Input component usable across all apps |
| AC4 | turbo.json defines build, dev, lint, and test pipelines with correct dependency ordering |
| AC5 | Each app has its own tsconfig.json extending a shared base config in packages/typescript-config |
| AC6 | pnpm-workspace.yaml correctly lists all workspace packages |
| AC7 | Root .gitignore excludes node_modules, .env files, .next, and turbo cache |
| AC8 | Root .env.example committed with ALL required variable names across all apps — includes DATABASE_URL, STRIPE_SECRET_KEY, STRIPE_WEBHOOK_SECRET, CLERK_SECRET_KEY (x2), RESEND_API_KEY, INNGEST_SIGNING_KEY, INNGEST_EVENT_KEY, UPSTASH_REDIS_REST_URL, UPSTASH_REDIS_REST_TOKEN, NEXT_PUBLIC_POSTHOG_KEY, ADMIN_EMAIL, ADMIN_PASSWORD |
| AC9 | Each app has its own .env.local.example documenting which vars are app-specific (e.g. NEXT_PUBLIC_STRIPE_PUBLISHABLE_KEY in apps/web) |
| AC10 | Root README.md documents: which env vars go in root .env vs app-specific .env.local, how to run all apps in dev, how to run a single app, and how to add a new shared package |

Technical Notes

- Use `pnpm create turbo` as the base, then customize apps and packages

- Each app deploys as a separate Vercel project — ensure vercel.json is present in each app

- Subdomains: web=joeperks.com, roaster=roasters.joeperks.com, org=orgs.joeperks.com, admin=admin.joeperks.com

- For local dev, use different ports. Subdomain routing tested with hosts file or ngrok

Definition of Done

- All four apps build successfully with `turbo build`

- Shared packages import correctly in at least one component per app

- PR merged with CI passing (lint + typecheck)

US-01-02 Complete Prisma schema with first migration against Neon

| Points | Priority | Status | Epic | Sprint |
| --- | --- | --- | --- | --- |
| 5 pts | High | Todo | EP-01 Infrastructure | Sprint 1 |

As a developer, I want to the complete Prisma schema deployed to Neon Postgres with all models, enums, indexes, and seed data so that all apps can immediately query the database with full type safety

Dependencies: US-01-01

Acceptance Criteria

| # | Acceptance Criteria |
| --- | --- |
| AC1 | `npx prisma migrate dev --name init` runs without errors against the Neon DATABASE_URL |
| AC2 | All 26 models are created: PlatformSettings, User, MagicLink, StripeEvent, EmailLog, OrderSequence, RoasterApplication, Roaster, RoasterShippingRate, RoasterDebt, OrgApplication, RoasterOrgRequest, Org, RoasterOrgRelationship, Product, ProductVariant, Campaign, CampaignItem, Cart, CartItem, Buyer, Order, OrderItem, DisputeRecord, OrderEvent, ApplicationEvent |
| AC3 | User model confirmed: fields external_auth_id (unique, maps to Clerk user ID), email (unique), role (UserRole enum), roaster_id (nullable FK), org_id (nullable FK), is_platform_admin (boolean), last_seen_at (nullable datetime) |
| AC4 | Buyer model confirmed: fields email (unique), name (nullable), orders relation — keyed on email, no password |
| AC5 | All enums are created: UserRole, ApplicationStatus, OrgApplicationStatus, RoasterOrgRequestStatus, RoasterStatus, OrgStatus, CampaignStatus, ProductStatus, StripeOnboardingStatus, OrderStatus, PayoutStatus, FulfillerType, LabelSource, MagicLinkPurpose, ActorType, OrgType, RoastLevel, GrindOption, FaultType, DisputeOutcome, DebtReason, OrderEventType |
| AC6 | Seed script creates PlatformSettings singleton and OrderSequence singleton with all default values |
| AC7 | Critical indexes are present: Order[roaster_id+status], Order[payout_status+payout_eligible_at], Order[status+fulfill_by], OrderEvent[order_id+event_type], RoasterDebt[roaster_id+settled], Cart[expires_at], ProductVariant[product_id+is_available], EmailLog[entity_id+template] |
| AC8 | Prisma Client generates without errors and types are exported from packages/db |

Technical Notes

- Schema source of truth: packages/db/schema.prisma — see DB Schema Reference document

- All monetary fields are Int (cents) — never Float

- product_subtotal and shipping_amount are separate fields on Order — never combined

- deleted_at DateTime? on Product and ProductVariant for soft deletes — queries always filter WHERE deleted_at IS NULL

- Order.org_pct_snapshot stores the org percentage at time of order — immutable after creation

- Order.roaster_id is explicit FK (not derived via CampaignItem → Product → Roaster) — this enables Phase 3 multi-roaster campaigns without schema change

- Phase 2 stubs: ProductReview model (order_id, variant_id, buyer_email, rating Int, comment String?, published Boolean) — add as commented block at bottom of schema.prisma so the structure is documented even though the table doesn't exist yet

Definition of Done

- Migration file committed to repo in prisma/migrations/

- Seed runs with `npx prisma db seed` without errors

- `prisma studio` opens and shows all 26 tables including User and Buyer

- Database recovery procedure documented in README.md: how to restore from Neon PITR, URL for Neon dashboard, who holds the DB credentials

US-01-03 Clerk authentication configured for roaster and org portals

| Points | Priority | Status | Epic | Sprint |
| --- | --- | --- | --- | --- |
| 5 pts | High | Todo | EP-01 Infrastructure | Sprint 1 |

As a developer, I want to Clerk authentication installed and configured in apps/roaster and apps/org with middleware protecting all routes so that only authenticated users with the correct role can access their respective portal

Dependencies: US-01-01

Acceptance Criteria

| # | Acceptance Criteria |
| --- | --- |
| AC1 | Clerk publishable and secret keys configured in apps/roaster/.env.local and apps/org/.env.local |
| AC2 | middleware.ts in each app protects all routes except /onboarding/* and /sign-in |
| AC3 | ClerkProvider wraps the root layout in both apps |
| AC4 | Sign-in page redirects to /dashboard on success |
| AC5 | Unauthenticated users are redirected to /sign-in |
| AC6 | User role (ROASTER_ADMIN ¦ ORG_ADMIN) is stored in Clerk public metadata and synced to User table via webhook |
| AC7 | Admin app (apps/admin) uses a separate hardcoded credentials check via ADMIN_EMAIL and ADMIN_PASSWORD env vars — no Clerk dependency |

Technical Notes

- Use Clerk's Next.js App Router integration: `@clerk/nextjs`

- On user creation webhook (user.created): create User record in DB linked to roaster_id or org_id

- Roaster and org portals are separate Clerk applications with separate API keys

- Admin uses HTTP Basic Auth via Next.js middleware for MVP — upgrade to Clerk in Phase 2

Definition of Done

- Signing in as a roaster shows roaster portal, signing in as an org shows org portal

- Attempting to access /dashboard without auth redirects to /sign-in

- User record created in DB on first sign-in

US-01-04 Resend + React Email infrastructure with base templates

| Points | Priority | Status | Epic | Sprint |
| --- | --- | --- | --- | --- |
| 5 pts | High | Todo | EP-01 Infrastructure | Sprint 1 |

As a developer, I want to Resend configured in packages/email with a base email layout and EmailLog writes on every send so that any app can send a typed, branded transactional email and every send is recorded for deduplication

Dependencies: US-01-02

Acceptance Criteria

| # | Acceptance Criteria |
| --- | --- |
| AC1 | packages/email exports a `sendEmail(template, to, props)` function usable from any app |
| AC2 | Base email layout component exists with Joe Perks header, footer, and brand colors |
| AC3 | Every send writes an EmailLog record before calling Resend — duplicate sends for same entity+template are blocked |
| AC4 | Test email sends successfully to a real address and renders correctly in Gmail and Apple Mail |
| AC5 | RESEND_API_KEY stored in root .env and available to all apps via turbo pipeline |
| AC6 | React Email dev server (`email dev`) renders all templates in browser for local preview |
| AC7 | Failed sends are caught, logged to console with error details, and do NOT throw — degraded gracefully |

Technical Notes

- Use `resend` npm package + `@react-email/components` for template building

- EmailLog.provider_id stores the Resend message ID for support lookups

- Deduplication query: check EmailLog WHERE entity_id = X AND template = Y before sending

- Template list for MVP: order_confirmation, order_shipped, order_delivered, order_impact, magic_link_fulfillment, magic_link_org_approval, roaster_application_received, roaster_approved, org_application_received, org_approved, sla_reminder

Definition of Done

- All 11 MVP templates render without errors in React Email dev server

- Duplicate send protection verified by unit test

- EmailLog records visible in Prisma Studio after test send

US-01-05 Stripe keys, webhook endpoint, and idempotency handler

| Points | Priority | Status | Epic | Sprint |
| --- | --- | --- | --- | --- |
| 5 pts | High | Todo | EP-01 Infrastructure | Sprint 1 |

As a developer, I want to a verified Stripe webhook endpoint with signature checking and an idempotency guard using the StripeEvent table so that fake webhook events are rejected and duplicate events from Stripe retries are safely ignored

Dependencies: US-01-02

Acceptance Criteria

| # | Acceptance Criteria |
| --- | --- |
| AC1 | POST /api/webhooks/stripe exists in apps/web and verifies Stripe-Signature header using stripe.webhooks.constructEvent() |
| AC2 | Invalid signatures return HTTP 400 immediately — no processing occurs |
| AC3 | Valid events are checked against StripeEvent table — if stripe_event_id exists, return HTTP 200 immediately |
| AC4 | New events create a StripeEvent record before processing begins |
| AC5 | Raw body is available for signature verification — Next.js JSON parsing is bypassed for this route |
| AC6 | STRIPE_SECRET_KEY validation at startup: throws if key starts with sk_live_ and NODE_ENV !== production |
| AC7 | Stripe test mode keys work in development; live keys only in production Vercel deployment |

Technical Notes

- Use `export const config = { api: { bodyParser: false } }` or equivalent in App Router to get raw body

- In App Router: read raw body with `await req.arrayBuffer()` then pass Buffer to constructEvent

- Webhook secret stored as STRIPE_WEBHOOK_SECRET — separate for test and live environments

- packages/stripe exports stripe client instance initialized once and reused

Definition of Done

- Stripe CLI `stripe listen --forward-to localhost:3000/api/webhooks/stripe` processes events correctly

- Sending same event ID twice only creates one StripeEvent record

- Invalid signature test returns 400

US-01-06 Inngest configured with sla-check and payout-release job stubs

| Points | Priority | Status | Epic | Sprint |
| --- | --- | --- | --- | --- |
| 3 pts | Medium | Todo | EP-01 Infrastructure | Sprint 1 |

As a developer, I want to Inngest installed with a serve route and two stub jobs: sla-check (hourly) and payout-release (daily) so that background job infrastructure is in place from day one and jobs can be incrementally implemented

Dependencies: US-01-01

Acceptance Criteria

| # | Acceptance Criteria |
| --- | --- |
| AC1 | POST /api/inngest serves the Inngest handler in apps/web |
| AC2 | sla-check function exists and runs on cron `0 * * * *` — logs 'SLA check running' and exits cleanly |
| AC3 | payout-release function exists and runs on cron `0 9 * * *` — logs 'Payout release running' and exits cleanly |
| AC4 | Inngest Dev Server (`npx inngest-cli dev`) shows both functions registered |
| AC5 | INNGEST_SIGNING_KEY and INNGEST_EVENT_KEY stored in .env |

Technical Notes

- Use `inngest` npm package with Next.js App Router serve helper

- Both jobs are stubs — full implementation in EP-06

- Inngest free tier supports MVP volume; no payment required to launch

Definition of Done

- Both jobs appear in Inngest Dev Server dashboard

- Jobs can be triggered manually from Dev Server without errors

US-01-07 Sentry error monitoring on all four apps

| Points | Priority | Status | Epic | Sprint |
| --- | --- | --- | --- | --- |
| 3 pts | Medium | Todo | EP-01 Infrastructure | Sprint 1 |

As a developer, I want to Sentry installed and configured on all four Next.js apps with source maps and a test error verifying the integration so that any unhandled exception in production is immediately visible in Sentry with a full stack trace

Dependencies: US-01-01

Acceptance Criteria

| # | Acceptance Criteria |
| --- | --- |
| AC1 | Sentry is initialized in sentry.client.config.ts and sentry.server.config.ts in each app |
| AC2 | A test route /api/test-sentry throws a deliberate error that appears in Sentry within 30 seconds |
| AC3 | Source maps are uploaded on build so stack traces show original TypeScript source |
| AC4 | SENTRY_DSN is unique per app and stored in each app's environment variables |
| AC5 | PII scrubbing: beforeSend hook strips email, name, address1, address2, city, state, zip, phone, and card fields from all Sentry events |
| AC6 | Console.log statements in /api/checkout/create-intent and /api/webhooks/stripe are verified to NOT log req.body or any buyer fields — only structured log fields (order_id, stripe_pi_id, event_type) are logged |
| AC7 | A code review checklist item is added to the PR template: 'No PII (email, name, address, card data) logged in checkout or webhook routes' |
| AC8 | Vercel log drain reviewed: checkout and webhook routes confirmed not to emit buyer data in any log output |

Technical Notes

- Use @sentry/nextjs package with automatic instrumentation

- Stripe webhook failures and payout errors must trigger Sentry alerts — add explicit Sentry.captureException() in those handlers

Definition of Done

- Test error appears in Sentry with correct app name tag and TypeScript source location

US-01-08 Legal placeholder pages: /terms/roaster, /terms/org, /privacy-policy

| Points | Priority | Status | Epic | Sprint |
| --- | --- | --- | --- | --- |
| 2 pts | High | Todo | EP-01 Infrastructure | Sprint 1 |

As a platform admin, I want to static placeholder pages at /terms/roaster, /terms/org, and /privacy-policy in apps/web before any onboarding forms go live so that the roaster and org application forms can link to required legal documents, and the platform is not collecting applicant data without a reachable privacy policy

Dependencies: US-01-01

Acceptance Criteria

| # | Acceptance Criteria |
| --- | --- |
| AC1 | GET /terms/roaster returns a page with a prominent 'PENDING LEGAL REVIEW — Not yet effective' banner at the top |
| AC2 | GET /terms/org returns the same structure with org-specific placeholder content |
| AC3 | GET /privacy-policy returns a placeholder with the same banner |
| AC4 | All three pages include the Joe Perks header and footer matching the main site design |
| AC5 | Footer on all apps/web pages includes links to /terms/roaster, /terms/org, and /privacy-policy |
| AC6 | Storefront footer at joeperks.com/[slug] links to /privacy-policy and a generic /terms page |
| AC7 | Pages return HTTP 200 — not 404 or 302 redirect |
| AC8 | A README note is added: 'Legal content must be reviewed by counsel and PENDING banner removed before first real-money order is processed' |

Technical Notes

- These are static Next.js pages — no DB queries, no auth required

- Content is placeholder only. Actual legal language requires attorney review before launch

- The 'PENDING LEGAL REVIEW' banner must be visually prominent — red background, not subtle

- Phase 2: replace placeholder content with attorney-reviewed terms once complete

- Failure to have these pages live before onboarding forms launch is a compliance risk under CCPA and general data collection laws

Definition of Done

- All three pages reachable via browser with correct HTTP 200

- Footer links verified on storefront, roaster application, and org application pages

- PENDING banner visible without scrolling on each page

US-01-09 Rate limiting infrastructure via Upstash Redis on checkout and onboarding endpoints

| Points | Priority | Status | Epic | Sprint |
| --- | --- | --- | --- | --- |
| 3 pts | High | Todo | EP-01 Infrastructure | Sprint 1 |

As a platform, I want to rate limiting applied to the checkout PaymentIntent endpoint and both onboarding form submission endpoints using Upstash Redis so that stolen credit card testing (carding attacks) cannot use our checkout as a validator, and spam submissions cannot flood our application queues

Dependencies: US-01-01

Acceptance Criteria

| # | Acceptance Criteria |
| --- | --- |
| AC1 | Upstash Redis account created, REST URL and token stored as UPSTASH_REDIS_REST_URL and UPSTASH_REDIS_REST_TOKEN in root .env and .env.example |
| AC2 | @upstash/ratelimit and @upstash/redis packages installed in packages/stripe or a new packages/ratelimit package |
| AC3 | POST /api/checkout/create-intent: limited to 5 requests per hour per IP address — returns HTTP 429 with body { error: 'Too many requests. Please try again later.' } when exceeded |
| AC4 | POST on roaster application form submission (US-02-01): limited to 3 requests per hour per IP — returns 429 on excess |
| AC5 | POST on org application form submission (US-03-01): limited to 3 requests per hour per IP — returns 429 on excess |
| AC6 | Magic link generation endpoint: limited to 10 requests per hour per roaster_id — prevents token flooding |
| AC7 | Rate limit key for checkout uses X-Forwarded-For header with fallback to connection remote address — handles proxy/CDN correctly |
| AC8 | Rate limit exceeded events are logged to Sentry with IP and endpoint for security monitoring |
| AC9 | 429 responses on the checkout form show a user-friendly message: 'Too many attempts. Please wait a few minutes and try again' — not a raw JSON error |
| AC10 | UPSTASH_REDIS_REST_URL and UPSTASH_REDIS_REST_TOKEN added to .env.example with instructions |

Technical Notes

- Use @upstash/ratelimit sliding window algorithm — more accurate than fixed window for abuse prevention

- Upstash free tier supports 10,000 requests/day — sufficient for MVP volume

- Rate limiter should be initialized once as a module-level singleton, not per-request

- Example: const ratelimit = new Ratelimit({ redis: Redis.fromEnv(), limiter: Ratelimit.slidingWindow(5, '1 h') })

- Do NOT rate limit the Stripe webhook endpoint — Stripe retries legitimately and must not be blocked

- Carding attacks are the primary financial risk at launch — this story is non-negotiable for any public checkout

Definition of Done

- curl loop sending 10 POST requests to /api/checkout/create-intent from same IP — 6th request returns 429

- Same test on roaster/org application endpoints — 4th request returns 429

- Sentry alert received for rate limit breach

US-01-10 Cart cleanup Inngest stub job and Posthog analytics scaffold

| Points | Priority | Status | Epic | Sprint |
| --- | --- | --- | --- | --- |
| 2 pts | Medium | Todo | EP-01 Infrastructure | Sprint 1 |

As a developer, I want to a registered cart-cleanup Inngest job stub and Posthog initialized in apps/web so that the Cart table doesn't accumulate stale rows indefinitely and storefront conversion data is captured from the first order

Dependencies: US-01-06  ·  US-01-01

Acceptance Criteria

| # | Acceptance Criteria |
| --- | --- |
| AC1 | cart-cleanup Inngest function registered, runs on cron '0 2 * * *' (daily 02:00 UTC) |
| AC2 | Stub implementation: logs count of carts WHERE expires_at < now() — does NOT delete yet (Phase 2 implementation) |
| AC3 | Function appears in Inngest Dev Server alongside sla-check and payout-release |
| AC4 | Posthog JS SDK installed in apps/web: `@/app/providers.tsx` wraps layout with PosthogProvider |
| AC5 | NEXT_PUBLIC_POSTHOG_KEY and NEXT_PUBLIC_POSTHOG_HOST added to apps/web/.env.local.example |
| AC6 | Posthog initialized with autocapture disabled — only explicit events tracked (no accidental PII capture) |
| AC7 | posthog.capture() calls added: storefront_viewed (on page load with slug + org_name), product_added_to_cart (with product_name + price — NO email or address), checkout_started, checkout_completed (with order_number + total_cents — NO buyer PII) |
| AC8 | Posthog events verified in Posthog dashboard after test purchase in development |
| AC9 | No PII (email, name, address, phone) appears in any Posthog event property — verified by code review checklist item |

Technical Notes

- Posthog free tier: 1M events/month — more than sufficient for MVP

- Autocapture must be disabled: posthog.init(key, { autocapture: false }) — autocapture would record form field values including potentially addresses

- Cart cleanup full implementation (actual DELETE) deferred to Phase 2 when DB-backed cart is built

- The cart cleanup stub is important because: when Phase 2 adds the real implementation, the job already exists and is deployed — no new Inngest function registration needed

- Posthog is the data you need to answer: what % of storefront visitors add to cart? what % who start checkout complete it? which products convert best?

Definition of Done

- cart-cleanup appears in Inngest Dev Server and runs without error

- storefront_viewed event appears in Posthog after visiting test storefront

- checkout_completed event appears in Posthog after test purchase with no PII in properties

EP-02 · Roaster Onboarding & Products 42 story points · 6 stories · Sprint 2

Roaster application form, admin approval queue, Stripe Connect onboarding, product/variant catalog setup with live margin preview, and shipping rate configuration with availability guard.

US-02-01 Roaster application form (5 steps) on main site

| Points | Priority | Status | Epic | Sprint |
| --- | --- | --- | --- | --- |
| 8 pts | High | Todo | EP-02 Roaster Onboarding | Sprint 2 |

As a prospective roaster, I want to to complete a multi-step application form at joeperks.com/roasters/apply so that I can apply to join the Joe Perks platform and have my application reviewed by the admin team

Dependencies: US-01-02  ·  US-01-04

Acceptance Criteria

| # | Acceptance Criteria |
| --- | --- |
| AC1 | Form has 5 steps: Business Basics, Roasting Operation, Product Preview, Mission Alignment, Confirm & Submit |
| AC2 | Progress indicator shows current step and completed steps |
| AC3 | Each step validates required fields before allowing Next — validation errors shown inline |
| AC4 | Step data persists in React state across navigation (back/forward between steps works without data loss) |
| AC5 | Step 3 (Product Preview) collects: estimated product count, price range min/max, specialty offerings (yes/no), seasonal offerings (yes/no) |
| AC6 | Step 4 (Mission Alignment) collects: why join Joe Perks (textarea), preferred_causes (multi-select checkboxes), excluded_causes (multi-select checkboxes) |
| AC7 | Step 5 shows a full summary of all entered data before submission |
| AC8 | Step 5 includes checkbox: 'I agree to the Joe Perks Roaster Terms' with link to /terms/roaster — submission blocked if unchecked |
| AC9 | On submit: RoasterApplication record created with status PENDING_REVIEW, terms_agreed_at and terms_version set |
| AC10 | On submit: confirmation email sent to applicant using order_confirmation template stub |
| AC11 | On submit: ApplicationEvent logged with from_status=null, to_status=PENDING_REVIEW, actor_type=SYSTEM |
| AC12 | Duplicate email check: if email already exists in RoasterApplication or Roaster, show 'An application with this email already exists' |
| AC13 | Rate limiting: form submission endpoint returns HTTP 429 after 3 requests from same IP within 1 hour — shows 'Too many submissions. Please try again later.' inline error (via US-01-09 infrastructure) |

Technical Notes

- Use React state + URL search params for step navigation (step=1, step=2, etc.) so browser back button works

- No authentication required — public form

- Ship_states field: multi-select US state picker, only shown if ships_nationally = false

- terms_version stored as a string e.g. '2026-03-01' — bump when terms change

Definition of Done

- Submitted application appears in Prisma Studio with all fields populated

- Confirmation email received at test address

- ApplicationEvent row created with correct status transition

US-02-02 Admin approval queue for roaster applications

| Points | Priority | Status | Epic | Sprint |
| --- | --- | --- | --- | --- |
| 5 pts | High | Todo | EP-02 Roaster Onboarding | Sprint 2 |

As a platform admin, I want to to see all pending roaster applications in an approval queue with all submitted details so that I can review each application and approve or reject it with a single click

Dependencies: US-02-01  ·  US-01-03

Acceptance Criteria

| # | Acceptance Criteria |
| --- | --- |
| AC1 | Admin dashboard at admin.joeperks.com/approvals/roasters shows all PENDING_REVIEW applications, sorted newest first |
| AC2 | Each application row shows: business name, contact name, email, city/state, submitted date, and Approve / Reject buttons |
| AC3 | Clicking an application row expands a detail panel showing all submitted fields including mission statement and cause preferences |
| AC4 | Approve action: creates Roaster record, creates Stripe Express account, sends Stripe onboarding link email to roaster, logs ApplicationEvent (PENDING_REVIEW → APPROVED) |
| AC5 | Reject action: prompts admin for a rejection reason (required), sends rejection email to applicant, logs ApplicationEvent (PENDING_REVIEW → REJECTED) |
| AC6 | Approved applications move to an Approved tab; rejected to a Rejected tab |
| AC7 | Admin name (from session) stored as reviewed_by on the application |
| AC8 | Queue shows count badge: 'Pending (3)' |

Technical Notes

- Admin app uses hardcoded HTTP Basic Auth for MVP — no Clerk required

- Stripe account creation: `stripe.accounts.create({ type: 'express', email, metadata: { roaster_application_id } })`

- Store stripe_account_id on Roaster record immediately — onboarding link is generated fresh each time it's needed

Definition of Done

- Approving a test application creates Roaster row and Stripe Express account in test mode

- Rejection email received at test address with reason included

- ApplicationEvent records show correct status transitions

US-02-03 Stripe Connect Express onboarding for roasters

| Points | Priority | Status | Epic | Sprint |
| --- | --- | --- | --- | --- |
| 5 pts | High | Todo | EP-02 Roaster Onboarding | Sprint 2 |

As a approved roaster, I want to to complete Stripe's KYC and bank account onboarding via a link sent to my email so that I can receive payouts from Joe Perks for fulfilled orders

Dependencies: US-02-02

Acceptance Criteria

| # | Acceptance Criteria |
| --- | --- |
| AC1 | Roaster receives email with a 'Complete your payment setup' link to Stripe's hosted onboarding flow |
| AC2 | Stripe onboarding link is generated fresh from stripe.accountLinks.create() — never stored in DB |
| AC3 | After completing Stripe onboarding, roaster is redirected to roasters.joeperks.com/onboarding/complete |
| AC4 | account.updated webhook fires and syncs charges_enabled and payouts_enabled to Roaster record |
| AC5 | Roaster status changes from ONBOARDING to ACTIVE when both charges_enabled and payouts_enabled are true |
| AC6 | Roaster portal dashboard is accessible only when status = ACTIVE |
| AC7 | If roaster revisits onboarding link after 5-minute expiry, a 'Resend setup link' page at /onboarding/refresh generates a fresh link |

Technical Notes

- account.updated webhook: check event.data.object.charges_enabled && payouts_enabled before updating status

- Refresh URL: GET roasters.joeperks.com/onboarding/refresh — generates new accountLink and redirects

- Return URL: roasters.joeperks.com/onboarding/complete — show 'Setup complete, loading your dashboard...' then redirect

Definition of Done

- Full end-to-end test: application → approval → Stripe onboarding → status = ACTIVE

- Roaster dashboard accessible after onboarding complete

US-02-04 Product and variant creation with wholesale/retail pricing and margin preview

| Points | Priority | Status | Epic | Sprint |
| --- | --- | --- | --- | --- |
| 8 pts | High | Todo | EP-02 Roaster Onboarding | Sprint 2 |

As a active roaster, I want to to create products with variants (size + grind combinations), set wholesale and retail prices, and see a live margin preview so that I understand exactly what I will earn per unit before publishing a product to campaigns

Dependencies: US-02-03

Acceptance Criteria

| # | Acceptance Criteria |
| --- | --- |
| AC1 | Product form collects: name (required), description, origin (text field), roast level (LIGHT/MEDIUM/MEDIUM_DARK/DARK dropdown), image upload |
| AC2 | Each product has at least one variant; variants are added inline on the product form |
| AC3 | Variant form collects: size_oz (8/12/16/32 selector), grind (WHOLE_BEAN/GROUND_DRIP/GROUND_ESPRESSO/GROUND_FRENCH_PRESS), wholesale_price, retail_price |
| AC4 | Wholesale price is optional — toggle 'Offer wholesale pricing' defaults wholesale to retail if off |
| AC5 | Live margin preview updates on every price change: shows buyer pays / org cut (15% example) / platform fee (5%) / Stripe fee / roaster net — all in dollars |
| AC6 | Platform enforces: retail_price >= wholesale_price * 1.10 — shows error 'Retail price must be at least 10% above wholesale' if violated |
| AC7 | Products save as DRAFT — a separate 'Publish' button changes status to ACTIVE |
| AC8 | Published products appear in the roaster's product list with an ACTIVE badge |
| AC9 | Soft delete: archive button sets deleted_at — product disappears from list but FK relationships preserved |
| AC10 | Roaster can only see their own products — queries scoped by roaster_id from session |

Technical Notes

- Image upload: use Uploadthing for MVP, store URL in product.image_url

- Margin preview reads platform_fee_pct and platform_fee_floor from PlatformSettings singleton

- Variant SKU is optional at creation — auto-generated as ROASTER_ID-PRODUCT_ID-SIZE-GRIND if left blank

- No product approval workflow at MVP — roasters self-publish

Definition of Done

- Product with 3 variants published, all visible in Prisma Studio with correct prices

- Margin preview matches manual calculation at test prices

- Retail < wholesale*1.10 validation blocks publish with correct error message

US-02-05 Roaster shipping rate configuration

| Points | Priority | Status | Epic | Sprint |
| --- | --- | --- | --- | --- |
| 5 pts | High | Todo | EP-02 Roaster Onboarding | Sprint 2 |

As a active roaster, I want to to set flat shipping rates for standard and express delivery in my portal so that buyers are charged the correct shipping amount at checkout and I receive that amount in full

Dependencies: US-02-04

Acceptance Criteria

| # | Acceptance Criteria |
| --- | --- |
| AC1 | Shipping rates page at /settings/shipping shows all existing rates with edit/delete actions |
| AC2 | Add rate form collects: label (e.g. 'Standard 3–5 days'), carrier (optional), flat_rate in dollars (stored as cents) |
| AC3 | One rate can be marked as default — shown first at checkout |
| AC4 | Minimum one rate required before roaster products can appear in any campaign |
| AC5 | Delete shows confirmation: 'This will remove this shipping option from all active campaigns — confirm?' |
| AC6 | Rates are scoped to roaster — only visible to the authenticated roaster who created them |

Technical Notes

- Phase 2: carrier_account_id added to this table for platform-generated labels via EasyPost

- Shipping rate is passed through 100% — platform fee and org % never applied to shipping_amount

Definition of Done

- Two rates (standard + express) created for test roaster

- Default rate appears first in list

US-02-06 Slug reservation blocklist validation

| Points | Priority | Status | Epic | Sprint |
| --- | --- | --- | --- | --- |
| 3 pts | Medium | Todo | EP-02 Roaster Onboarding | Sprint 2 |

As a platform admin, I want to org slugs to be validated against a reserved blocklist before being accepted so that organizations cannot claim slugs that would conflict with platform routes or be inappropriate

Dependencies: US-01-02

Acceptance Criteria

| # | Acceptance Criteria |
| --- | --- |
| AC1 | RESERVED_SLUGS constant in packages/types includes at minimum: api, admin, checkout, roasters, orgs, app, www, mail, help, support, terms, privacy, about, how-it-works, apply, sign-in, sign-up, dashboard, settings, products, orders, campaigns, payouts |
| AC2 | Slug validation function: lowercase alphanumeric and hyphens only, 3–40 chars, not in reserved list |
| AC3 | Validation runs on the org application form (client-side for UX + server-side for security) |
| AC4 | Duplicate check: if slug already exists in Org or OrgApplication, return 'This URL is already taken' |
| AC5 | All validation errors shown inline next to the slug field |

Technical Notes

- Same validation function used in org application form (US-03-01) and admin approval flow

Definition of Done

- Unit tests cover: valid slug, reserved slug, duplicate slug, invalid chars, too short, too long

EP-03 · Org Onboarding & Approval Chain 38 story points · 4 stories · Sprint 2–3

Org application form, platform admin review, roaster approval magic link flow, Stripe Connect for org payouts, campaign setup.

US-03-01 Org application form (5 steps) on main site

| Points | Priority | Status | Epic | Sprint |
| --- | --- | --- | --- | --- |
| 8 pts | High | Todo | EP-03 Org Onboarding | Sprint 2 |

As a prospective org admin, I want to to complete a multi-step application form at joeperks.com/orgs/apply so that my organization can be reviewed and approved to run a Joe Perks coffee fundraiser

Dependencies: US-01-02  ·  US-01-04  ·  US-02-06

Acceptance Criteria

| # | Acceptance Criteria |
| --- | --- |
| AC1 | Form has 5 steps: Organization Basics, Your Cause, Roaster Preference, Campaign Setup, Confirm & Submit |
| AC2 | Step 2 (Your Cause) collects: mission (short description, max 200 chars), fund_usage (how funds used, max 400 chars), fundraising_goal (optional dollar amount), campaign end date (optional) |
| AC3 | Step 3 (Roaster Preference) shows a browseable list of ACTIVE roasters filtered by state — card shows roaster name, city, and cause preferences |
| AC4 | Step 3 allows selecting up to 2 roasters: primary (priority=1) and backup (priority=2) |
| AC5 | Step 3 includes checkbox: 'Open to platform suggestion if preferred roaster is unavailable' |
| AC6 | Step 4 (Campaign Setup) collects: desired_slug (validated per US-02-06), desired_org_pct (slider 5–25%, default 15%), logo upload (optional) |
| AC7 | Step 4 shows live impact calculator: 'At 15%, a $20 bag earns your org $3.00' |
| AC8 | On submit: OrgApplication created with status PENDING_PLATFORM_REVIEW, RoasterOrgRequest records created for each selected roaster |
| AC9 | Confirmation email sent to applicant |
| AC10 | Duplicate email check with helpful error message |
| AC11 | Rate limiting: form submission endpoint returns HTTP 429 after 3 requests from same IP within 1 hour (via US-01-09 infrastructure) |

Technical Notes

- Roaster list shows only ACTIVE roasters with charges_enabled = true

- Impact calculator reads org_pct_min/max from PlatformSettings

Definition of Done

- OrgApplication with two RoasterOrgRequest records in Prisma Studio

- Confirmation email received

US-03-02 Admin org approval queue with routing to roaster review

| Points | Priority | Status | Epic | Sprint |
| --- | --- | --- | --- | --- |
| 5 pts | High | Todo | EP-03 Org Onboarding | Sprint 3 |

As a platform admin, I want to to review org applications and route approved ones to the selected roaster for their approval so that orgs are vetted by both the platform and the roaster they want to work with before going live

Dependencies: US-03-01  ·  US-02-02

Acceptance Criteria

| # | Acceptance Criteria |
| --- | --- |
| AC1 | Org queue at admin.joeperks.com/approvals/orgs shows PENDING_PLATFORM_REVIEW applications |
| AC2 | Detail panel shows all org application fields plus the selected roasters |
| AC3 | Platform approve action: changes status to PENDING_ROASTER_APPROVAL, creates MagicLink for roaster approval, sends roaster approval request email |
| AC4 | Platform reject action: requires reason, sends rejection email, logs ApplicationEvent |
| AC5 | Each roaster receives a separate email with magic link to approve/decline this specific org |
| AC6 | Applications in PENDING_ROASTER_APPROVAL state show 'Awaiting roaster response — sent [date]' with a 'Resend' button |
| AC7 | ApplicationEvent logged for every status transition |

Technical Notes

- MagicLink purpose = ROASTER_REVIEW, payload = { org_application_id, roaster_id }

- Primary roaster contacted first; if they decline, backup roaster contacted automatically

Definition of Done

- Magic link email received by test roaster email

- ApplicationEvent shows PENDING_PLATFORM_REVIEW → PENDING_ROASTER_APPROVAL

US-03-03 Roaster magic link approval/decline of org

| Points | Priority | Status | Epic | Sprint |
| --- | --- | --- | --- | --- |
| 5 pts | High | Todo | EP-03 Org Onboarding | Sprint 3 |

As a active roaster, I want to to click a link in my email and approve or decline an org that wants to work with me so that I have full control over which causes my coffee is associated with

Dependencies: US-03-02  ·  US-01-04

Acceptance Criteria

| # | Acceptance Criteria |
| --- | --- |
| AC1 | Magic link URL: roasters.joeperks.com/org-requests/[token] |
| AC2 | Page shows: org name, org type, city/state, mission statement, fund usage, fundraising goal, campaign slug preview |
| AC3 | Page shows roaster's earning preview: 'At their requested 15%, you earn $14.XX per $20 bag after fees' |
| AC4 | Two buttons: 'Approve this organization' and 'Decline (with optional note)' |
| AC5 | Token validated: must exist, not expired, not used_at already set |
| AC6 | On approve: RoasterOrgRequest status = APPROVED, used_at set on MagicLink, admin notified, proceeds to final admin approval step |
| AC7 | On decline: RoasterOrgRequest status = DECLINED, roaster_note saved, backup roaster contacted if available, org notified with 'preferred roaster unavailable' message and option to reselect |
| AC8 | Expired token: show 'This link has expired — please contact Joe Perks to request a new one' |
| AC9 | Already-used token: show 'You have already responded to this request' |

Technical Notes

- Page accessible WITHOUT authentication — magic link IS the auth for this action

- After roaster approves: if all required roasters have approved (for MVP = 1), trigger final admin approval

- Log ApplicationEvent: actor_type=ROASTER, actor_id=roaster.id

Definition of Done

- Full approval flow tested end-to-end: admin approves → roaster gets email → clicks link → approves → org activated

- Decline triggers backup roaster notification

- Expired token shows correct error page

US-03-04 Org Stripe Connect onboarding and campaign creation

| Points | Priority | Status | Epic | Sprint |
| --- | --- | --- | --- | --- |
| 5 pts | High | Todo | EP-03 Org Onboarding | Sprint 3 |

As a approved org admin, I want to to connect my bank account via Stripe and create my first fundraising campaign so that I can receive my fundraiser payouts and launch my storefront

Dependencies: US-03-03  ·  US-02-03

Acceptance Criteria

| # | Acceptance Criteria |
| --- | --- |
| AC1 | Approved org admin receives 'You're approved!' email with link to orgs.joeperks.com/onboarding |
| AC2 | Onboarding flow: complete Stripe Express account setup (same flow as roaster) then create first campaign |
| AC3 | Campaign creation form: name, description, goal amount (optional), end date (optional), org_pct (slider 5–25% with impact preview) |
| AC4 | Product selection: browse available products from linked roaster(s), add to campaign with drag-to-reorder and featured toggle |
| AC5 | Campaign slug is pre-filled from application desired_slug but editable (re-validated on change) |
| AC6 | On campaign publish: Campaign status = ACTIVE, storefront at joeperks.com/[slug] goes live |
| AC7 | Org dashboard shows: campaign status, storefront link, total raised ($0), and a 'Share your campaign' section with copyable link |

Technical Notes

- CampaignItem prices snapshotted from ProductVariant at campaign creation — changes to variant prices don't affect active campaign

- RoasterOrgRelationship record created when org campaign first goes ACTIVE

Definition of Done

- Storefront at joeperks.com/[slug] returns 200 with correct org branding and products

- CampaignItem records in DB with frozen prices

EP-04 · Buyer Storefront & Cart 38 story points · 5 stories · Sprint 3

Public org-slug storefront, product grid, Zustand cart with mobile bottom sheet, three-step checkout with Stripe Elements and rate limiting, analytics instrumentation. Updated to include US-04-05 Posthog story from gap audit.

US-04-01 Public org storefront at joeperks.com/[slug]

| Points | Priority | Status | Epic | Sprint |
| --- | --- | --- | --- | --- |
| 8 pts | High | Todo | EP-04 Storefront & Cart | Sprint 3 |

As a buyer, I want to to visit an org's storefront page and see their campaign story, fundraising progress, and available coffee products so that I understand what I'm supporting and can browse products before deciding to purchase

Dependencies: US-03-04

Acceptance Criteria

| # | Acceptance Criteria |
| --- | --- |
| AC1 | Server component at app/[slug]/page.tsx fetches campaign with all items, org, and roaster data |
| AC2 | Page renders without client-side loading spinners — server rendered HTML |
| AC3 | Storefront shows: org logo, org name, campaign description, fundraising goal progress bar (if goal set), roaster attribution |
| AC4 | Product grid shows all ACTIVE CampaignItems ordered by is_featured desc then sort_order asc |
| AC5 | Each product card shows: image, name, origin, roast level, size/grind selector, retail price, 'Add to Cart' button |
| AC6 | If campaign status is ENDED: show 'This campaign has ended. Total raised: $X' — no products shown, no checkout |
| AC7 | If campaign status is PAUSED: show 'This campaign is temporarily paused' — no products shown |
| AC8 | If org slug not found or campaign not ACTIVE/ENDED: return Next.js notFound() (404 page) |
| AC9 | If roaster linked to campaign has zero active RoasterShippingRates: show 'Shipping setup in progress — check back soon' instead of product grid (see US-04-05 for full guard logic) |
| AC10 | Page is mobile-first responsive — tested at 375px, 768px, 1280px |
| AC11 | Impact message visible on page: 'Every bag you buy raises $X for [Org Name]' calculated from org_pct |
| AC12 | Meta tags: title, description, and og:image set for social sharing |

Technical Notes

- Use Next.js generateMetadata() for dynamic meta tags per org

- Server component fetches from DB directly — no API route needed for initial render

- Image optimization: use next/image with Cloudflare R2 domain in next.config.js

Definition of Done

- Lighthouse score >= 90 on mobile

- Page renders correctly with no JS for SSR test

- 404 returned for unknown slugs

US-04-02 Zustand cart with add, remove, quantity update, and localStorage persistence

| Points | Priority | Status | Epic | Sprint |
| --- | --- | --- | --- | --- |
| 5 pts | High | Todo | EP-04 Storefront & Cart | Sprint 3 |

As a buyer, I want to to add products to a cart that persists across page reloads and shows a running total and fundraiser impact so that I can browse and build my order without losing my selections

Dependencies: US-04-01

Acceptance Criteria

| # | Acceptance Criteria |
| --- | --- |
| AC1 | useCart Zustand store exported from packages/ui/store/cart.ts with: campaign_id, items[], addItem, removeItem, updateQty, clear, subtotal() functions |
| AC2 | Cart persists to localStorage under key 'jp-cart' using zustand/middleware persist |
| AC3 | Adding item to cart for a different campaign_id clears existing cart and shows 'Your cart was updated for [new org name]' toast |
| AC4 | Cart drawer opens from right side on desktop, slides up from bottom on mobile |
| AC5 | Cart drawer shows: item list with name/variant/qty/price, subtotal, estimated org fundraiser amount, shipping note ('calculated at checkout') |
| AC6 | Fundraiser impact line: 'This order will raise $X.XX for [Org Name]' updates live with cart changes |
| AC7 | Qty controls: increment, decrement (removes item if 1→0), and direct number input |
| AC8 | Empty cart state: 'Your cart is empty — browse our coffees above' with a shop link |
| AC9 | Cart item count shown as badge on cart icon in storefront header |
| AC10 | Cart drawer renders as a bottom sheet (slides up from bottom edge) on screens narrower than 768px — not a side drawer |
| AC11 | All cart touch targets (add/remove buttons, quantity controls, close button) are minimum 44x44px for mobile usability |

Technical Notes

- unit_price in cart items is snapshot from CampaignItem.retail_price at add-to-cart time

- subtotal() returns sum of unit_price * quantity in cents

- Fundraiser impact = subtotal() * campaign.org_pct — read from campaign prop passed to CartDrawer

Definition of Done

- Cart survives page refresh with correct items

- Cross-campaign clear works and shows toast

- Cart drawer opens on mobile at correct breakpoint

US-04-03 Three-step checkout: cart review, shipping details, Stripe Elements payment

| Points | Priority | Status | Epic | Sprint |
| --- | --- | --- | --- | --- |
| 8 pts | High | Todo | EP-04 Storefront & Cart | Sprint 3 |

As a buyer, I want to to complete a checkout in three clear steps without leaving the storefront page so that I can purchase coffee and contribute to the cause with a seamless, mobile-friendly experience

Dependencies: US-04-02  ·  US-01-05

Acceptance Criteria

| # | Acceptance Criteria |
| --- | --- |
| AC1 | Checkout has three steps on /[slug]/checkout: Step 1 (Cart Review), Step 2 (Shipping), Step 3 (Payment) |
| AC2 | Step 1: shows final cart, shipping rate selector (populated from roaster's RoasterShippingRate), order total breakdown including fundraiser amount |
| AC3 | Step 2: collects buyer_name, buyer_email, ship_to_name, ship_to_address1, ship_to_address2 (optional), ship_to_city, ship_to_state, ship_to_zip — all required except address2 |
| AC4 | On Step 2 submit: POST /api/checkout/create-intent validates cart items server-side, calculates splits, creates PaymentIntent, creates pending Order record, returns client_secret |
| AC5 | Server-side validation: re-fetches CampaignItem prices from DB and rejects any mismatch with cart unit_prices |
| AC6 | Server-side validation: checks all items have is_available = true and campaign status = ACTIVE |
| AC7 | Step 3: renders Stripe Elements card input using client_secret from Step 2 |
| AC8 | Step 3: 'Place Order' button submits Stripe payment — shows loading spinner during processing |
| AC9 | On payment success: redirect to /[slug]/order/[payment_intent_id]?status=success |
| AC10 | On payment failure: show Stripe error message inline (e.g. 'Your card was declined') — do not navigate away |
| AC11 | Rate limiting: checkout create-intent endpoint limited to 5 requests/hour/IP via Upstash (via US-01-09 infrastructure) — returns 429 with user-friendly message in checkout UI |
| AC12 | ZIP code input field uses inputMode='numeric' to trigger numeric keyboard on mobile |
| AC13 | Phone number field (if present) uses inputMode='tel' |
| AC14 | All touch targets in checkout form are minimum 44px height |

Technical Notes

- Import Stripe Elements lazily (dynamic import) — only loaded when buyer reaches Step 3

- PaymentIntent metadata must include: campaign_id, roaster_id, org_id, order_id, and all split amounts

- calculateSplits() imported from packages/stripe — see DB Schema document for implementation

- buyer_ip captured from request headers and stored on Order for chargeback evidence

- CRITICAL: Do NOT log req.body anywhere in this route — it contains buyer address and email. Log only: order_id, campaign_id, stripe_pi_id, and total_cents

Definition of Done

- Full checkout flow tested in Stripe test mode — card 4242 4242 4242 4242 succeeds

- Card 4000 0000 0000 9995 shows decline error inline without navigation

- Order record in DB with status PENDING and all split amounts frozen

US-04-04 Order confirmation page with payment status polling

| Points | Priority | Status | Epic | Sprint |
| --- | --- | --- | --- | --- |
| 5 pts | High | Todo | EP-04 Storefront & Cart | Sprint 3 |

As a buyer, I want to to see a clear order confirmation page after payment that shows my order details and fundraiser impact so that I know my order was successful and feel good about the contribution I made

Dependencies: US-04-03

Acceptance Criteria

| # | Acceptance Criteria |
| --- | --- |
| AC1 | Page at /[slug]/order/[payment_intent_id] polls GET /api/order-status?pi=[id] every 2 seconds until order.status != PENDING |
| AC2 | While polling: show 'Confirming your order...' with a spinner — never show a confusing blank page |
| AC3 | Polling timeout: after 30 seconds without confirmation, show 'Your payment was received. You will receive a confirmation email shortly.' — stop polling |
| AC4 | On confirmation: show order number (JP-00001), items ordered, total paid, org fundraiser amount with message 'You just raised $X.XX for [Org Name]!', expected shipping carrier |
| AC5 | Show buyer email: 'A confirmation email has been sent to [email]' |
| AC6 | Cart is cleared on confirmed order |
| AC7 | 'Continue shopping' button returns to storefront |
| AC8 | Page is shareable — sharing /[slug]/order/[pi_id] shows the same confirmation for the same browser session (based on session check) |

Technical Notes

- order-status API route: find Order by stripe_pi_id, return { status, order_number, org_amount, org_name }

- Cart clear happens client-side on receiving confirmed status — not on page load

- Use React Query or SWR for polling with automatic retry

Definition of Done

- Confirmation page shows correct details within 10 seconds of payment

- Polling gracefully times out and shows fallback message

US-04-05 Shipping rate availability guard on storefront and campaign item activation

| Points | Priority | Status | Epic | Sprint |
| --- | --- | --- | --- | --- |
| 2 pts | Low | Todo | EP-04 Storefront & Cart | Sprint 3 |

As a buyer, I want to the storefront to show products only when the roaster has configured shipping so that I can never add a product to cart and proceed to checkout only to find no shipping option exists

Dependencies: US-02-05  ·  US-04-01

Acceptance Criteria

| # | Acceptance Criteria |
| --- | --- |
| AC1 | Storefront server component checks: roaster linked to campaign has at least one RoasterShippingRate with a flat_rate > 0 |
| AC2 | If roaster has zero active shipping rates: products section shows 'Shipping setup in progress — check back soon' message instead of product grid. Campaign story and fundraising goal bar still shown |
| AC3 | If roaster has at least one rate: normal product grid renders with shipping rate options in cart |
| AC4 | Org portal campaign setup page: 'Go Live' / 'Activate Campaign' button is disabled with tooltip 'Your roaster must configure shipping before this campaign can go live' if roaster has no rates |
| AC5 | Roaster portal products page: publishing a product shows a banner 'You must add a shipping rate before your products can appear in campaigns' if no rates exist — links to /settings/shipping |
| AC6 | Admin campaign list shows a 'No shipping configured' warning badge on campaigns where roaster has no rates |
| AC7 | Shipping rate check is cached for 5 minutes on the storefront — prevents DB query on every page view |

Technical Notes

- This guard prevents a silent failure mode: buyer adds to cart, hits checkout, no shipping options appear

- The check is roaster-scoped: if campaign has multiple roasters in Phase 3, each roaster's products are hidden independently if they have no rates

- Cache: use Next.js unstable_cache or React cache() with a 5-minute TTL for the shipping rate existence check

Definition of Done

- Test: remove all shipping rates from a roaster — their products disappear from storefront within 5 minutes

- Test: add a rate back — products reappear within 5 minutes

- Org campaign 'Go Live' button disabled with correct tooltip when roaster has no rates

EP-05 · Order Processing & Fulfillment 40 story points · 3 stories · Sprint 4

Stripe webhook handler, order creation with Buyer upsert, magic link fulfillment email, roaster marks shipped, buyer tracking notification.

US-05-01 payment_intent.succeeded webhook creates order and sends roaster magic link

| Points | Priority | Status | Epic | Sprint |
| --- | --- | --- | --- | --- |
| 8 pts | High | Todo | EP-05 Order Processing | Sprint 4 |

As a platform, I want to to handle the payment_intent.succeeded Stripe webhook by finalizing the order record and immediately notifying the roaster so that the roaster knows about the order within seconds of payment and can begin fulfillment

Dependencies: US-01-05  ·  US-04-03  ·  US-01-04

Acceptance Criteria

| # | Acceptance Criteria |
| --- | --- |
| AC1 | Webhook handler processes payment_intent.succeeded event |
| AC2 | Idempotency check: if StripeEvent.stripe_event_id exists, return 200 immediately |
| AC3 | Order found by stripe_pi_id — status updated from PENDING to CONFIRMED |
| AC4 | Order number generated atomically using OrderSequence: UPDATE OrderSequence SET next_val = next_val + 1 RETURNING next_val, formatted as JP-XXXXX |
| AC5 | fulfill_by set to created_at + 48 hours (from PlatformSettings.sla_breach_hours) |
| AC6 | OrderEvent created: ORDER_CREATED, actor_type=SYSTEM |
| AC7 | Buyer receives order confirmation email (see US-08-01) |
| AC8 | MagicLink created: purpose=ORDER_FULFILLMENT, actor_id=roaster.id, payload={ order_id }, expires_at = now + 72h |
| AC9 | Roaster receives magic link fulfillment email (see US-08-02) |
| AC10 | Buyer upsert: on order creation, db.buyer.upsert({ where: { email: buyer_email }, create: { email, name: buyer_name }, update: {} }) — link buyer.id to Order.buyer_id |
| AC11 | Webhook returns 200 within 5 seconds — all heavy processing is async or fast |
| AC12 | payment_intent.payment_failed: update Order status to CANCELLED, log OrderEvent, send buyer notification |
| AC13 | CRITICAL: Do NOT log event.data.object anywhere in full — it contains card fingerprints and buyer metadata. Log only: event.id, event.type, payment_intent_id, order_id |

Technical Notes

- Use Promise.all for parallel email sends — don't await sequentially

- Order number generation must be in a DB transaction to prevent race conditions

- stripe_charge_id extracted from payment intent: event.data.object.latest_charge

Definition of Done

- Order status = CONFIRMED within 10 seconds of test payment

- Roaster receives fulfillment email within 30 seconds

- OrderEvent record created with correct type and actor

US-05-02 Roaster magic link fulfillment page: view order and enter tracking

| Points | Priority | Status | Epic | Sprint |
| --- | --- | --- | --- | --- |
| 8 pts | High | Todo | EP-05 Order Processing | Sprint 4 |

As a roaster, I want to to click the link in my order notification email and see the full order details, then enter a tracking number to mark it as shipped so that I can fulfill the order without logging into any portal or learning a new system

Dependencies: US-05-01

Acceptance Criteria

| # | Acceptance Criteria |
| --- | --- |
| AC1 | Page at roasters.joeperks.com/fulfill/[token] — accessible WITHOUT authentication |
| AC2 | Token validation: exists, not expired, not used_at, purpose = ORDER_FULFILLMENT |
| AC3 | Order detail shows: order number, campaign name and org, all items (product name, variant, qty, unit price, line total), shipping address, estimated payout breakdown (your cut / org cut / platform fee / Stripe fee) |
| AC4 | Payout breakdown shows: 'Your net this order: $X.XX' prominently in green |
| AC5 | Tracking form: tracking number text input (required), carrier dropdown (UPS/FedEx/USPS/DHL/Other) |
| AC6 | On submit: Order status = SHIPPED, shipped_at = now, tracking_number and carrier saved, OrderEvent ORDER_SHIPPED created, MagicLink.used_at set, buyer notified (see US-08-03) |
| AC7 | After submit: page shows 'Order marked as shipped! Tracking: [number] via [carrier]' — no navigation away |
| AC8 | A 'Can't fulfill this order' link at bottom opens a modal to flag the issue to admin |
| AC9 | Flag modal: dropdown reason (Out of stock / Can't meet deadline / Other) + optional note → creates OrderEvent with flag payload, notifies admin |
| AC10 | Expired token: show 'This link has expired. Need help? Contact support@joeperks.com' |
| AC11 | Already-fulfilled: show 'This order has already been marked as shipped. [Tracking number] via [carrier]' |

Technical Notes

- After submit, issue a session cookie scoped to this roaster (via roaster.id from magic link) for the portal redirect nudge

- Phase 2: this page becomes the same order detail view inside the authenticated portal

Definition of Done

- Full end-to-end: payment → roaster email → magic link → tracking entry → buyer email with tracking

- Can't fulfill flag creates OrderEvent and admin sees it in order feed

US-05-03 Delivery confirmation and payout eligibility calculation

| Points | Priority | Status | Epic | Sprint |
| --- | --- | --- | --- | --- |
| 5 pts | High | Todo | EP-05 Order Processing | Sprint 4 |

As a platform, I want to to mark orders as delivered and calculate the payout_eligible_at date so that the payout job can release funds to roasters and orgs after the hold period

Dependencies: US-05-02

Acceptance Criteria

| # | Acceptance Criteria |
| --- | --- |
| AC1 | For MVP: delivery confirmed by carrier scan poll OR manual admin confirmation (admin can mark as delivered in order detail) |
| AC2 | On delivery: Order status = DELIVERED, delivered_at = now, OrderEvent ORDER_DELIVERED created |
| AC3 | payout_eligible_at = delivered_at + PlatformSettings.payout_hold_days (default 7 days) |
| AC4 | Buyer receives delivered + impact email (see US-08-04) |
| AC5 | Admin manual confirmation button at admin.joeperks.com/orders/[id]: 'Mark as Delivered' — requires admin session |
| AC6 | Mark as delivered disabled if order status is not SHIPPED |

Technical Notes

- Phase 2: replace admin manual confirmation with EasyPost/Aftership carrier webhook

- payout_eligible_at index on Order enables fast payout job queries

Definition of Done

- Marking as delivered sets correct payout_eligible_at (delivered_at + 7 days)

- Buyer impact email received

- OrderEvent ORDER_DELIVERED created

EP-06 · Payments, Payouts & Audit 36 story points · 3 stories · Sprint 4–5

Payout job with 7-day hold, roaster and org Stripe transfers, debt ledger, order event log, and chargeback webhook handling.

US-06-01 Inngest daily payout job: find eligible orders and create Stripe transfers

| Points | Priority | Status | Epic | Sprint |
| --- | --- | --- | --- | --- |
| 8 pts | High | Todo | EP-06 Payments & Payouts | Sprint 4 |

As a platform, I want to an automated daily job that finds all payout-eligible orders and creates Stripe transfers to roasters and orgs so that roasters and orgs are paid automatically without manual intervention

Dependencies: US-05-03  ·  US-01-06

Acceptance Criteria

| # | Acceptance Criteria |
| --- | --- |
| AC1 | payout-release Inngest job runs daily at 09:00 — queries Order WHERE payout_status=PENDING AND payout_eligible_at <= now() |
| AC2 | For each eligible order: check for unsettled RoasterDebt — deduct from roaster_amount before transfer |
| AC3 | Roaster transfer: stripe.transfers.create({ amount: net_roaster_amount, destination: roaster.stripe_account_id, source_transaction: stripe_charge_id, transfer_group: order.id, metadata: { order_id, type: 'roaster_payout' } }) |
| AC4 | Org transfer: stripe.transfers.create({ amount: org_amount, destination: org.stripe_account_id, source_transaction: stripe_charge_id, transfer_group: order.id, metadata: { order_id, type: 'org_payout' } }) |
| AC5 | On transfer success: Order.payout_status = TRANSFERRED, stripe_transfer_id and stripe_org_transfer saved, OrderEvent PAYOUT_TRANSFERRED created |
| AC6 | On transfer failure: Order.payout_status = FAILED, OrderEvent PAYOUT_FAILED created, Sentry alert fired, admin notified |
| AC7 | If net_roaster_amount = 0 (fully covered by debts): skip transfer, log event, settle applicable debts |
| AC8 | Debt settlement: update RoasterDebt.settled = true, settled_at = now() for fully settled debts |
| AC9 | Campaign.total_raised incremented by org_amount for each paid-out order |
| AC10 | Job processes orders in batches of 50 with 100ms delay between batches to avoid Stripe rate limits |

Technical Notes

- transfer_group is required on ALL transfers — enables reconciliation in Stripe dashboard

- Debt deduction logic: see calculateRoasterPayout() in DB Schema document

- RoasterDebt.settled updates must be in a transaction with the payout status update

Definition of Done

- Test order with 7-day hold: correct transfers created in Stripe test mode

- Test with RoasterDebt: net amount correctly deducted before transfer

- PAYOUT_TRANSFERRED OrderEvent created for both roaster and org transfers

US-06-02 Chargeback webhook handler with fault attribution and debt creation

| Points | Priority | Status | Epic | Sprint |
| --- | --- | --- | --- | --- |
| 8 pts | High | Todo | EP-06 Payments & Payouts | Sprint 5 |

As a platform, I want to to handle charge.dispute.created and charge.dispute.closed webhooks with automatic evidence compilation and fault-attributed debt creation so that chargebacks are surfaced immediately to admin, evidence is ready to submit, and roaster costs are recovered when it's their fault

Dependencies: US-06-01  ·  US-01-05

Acceptance Criteria

| # | Acceptance Criteria |
| --- | --- |
| AC1 | charge.dispute.created: creates DisputeRecord, sets respond_by = now + 7 days, updates Order to flag disputed, fires Sentry alert, creates OrderEvent DISPUTE_OPENED, admin dashboard shows red flag |
| AC2 | charge.dispute.created: if Order.payout_status = TRANSFERRED, sets payout_status = HELD on any pending related transfers |
| AC3 | Admin can set fault_attribution (ROASTER / PLATFORM / BUYER_FRAUD / UNCLEAR) on DisputeRecord from admin order detail page |
| AC4 | charge.dispute.closed with status=won: releases held transfers, creates OrderEvent DISPUTE_WON |
| AC5 | charge.dispute.closed with status=lost and fault=ROASTER: creates RoasterDebt records for roaster_amount + stripe_fee + dispute_fee_cents (from PlatformSettings), attempts transfer reversal, creates OrderEvent DISPUTE_LOST |
| AC6 | charge.dispute.closed with status=lost and fault=PLATFORM or BUYER_FRAUD: platform absorbs costs, creates OrderEvent DISPUTE_LOST, roaster payout protected |
| AC7 | RoasterDebt reasons: STRIPE_DISPUTE_FEE, STRIPE_PROCESSING_FEE_NONREFUNDABLE, CHARGEBACK_PAYOUT_RECOVERY |
| AC8 | After debt creation: checkRoasterDisputeThreshold() — if 3+ roaster-fault disputes in 90 days, set Roaster.status = SUSPENDED and notify admin |

Technical Notes

- Transfer reversal: stripe.transfers.createReversal(transfer_id) — wrapped in try/catch; if fails, all amounts go to RoasterDebt

- Dispute fee: PlatformSettings.dispute_fee_cents = 1500 — always roaster's cost if fault=ROASTER

Definition of Done

- Test chargeback created via Stripe test mode processed correctly

- Roaster-fault lost dispute creates correct RoasterDebt records totaling order amount + fees

- Admin sees dispute in dashboard with respond_by countdown

US-06-03 Order event log append-only writes and query API

| Points | Priority | Status | Epic | Sprint |
| --- | --- | --- | --- | --- |
| 5 pts | High | Todo | EP-06 Payments & Payouts | Sprint 4 |

As a developer, I want to a standardized logOrderEvent() helper and a query function that returns the full event history for any order so that every state change in the system is permanently recorded and can be exported for dispute evidence

Dependencies: US-01-02

Acceptance Criteria

| # | Acceptance Criteria |
| --- | --- |
| AC1 | logOrderEvent(orderId, eventType, actorType, actorId?, payload?, ipAddress?) function exported from packages/db |
| AC2 | Function creates OrderEvent record atomically — never throws on failure (logs to Sentry and returns null on error) |
| AC3 | getOrderTimeline(orderId) returns all events for an order sorted by created_at ascending |
| AC4 | getEvidencePackage(orderId) returns: order details, all events with timestamps, tracking info, buyer IP, and shipping confirmation — formatted as a plain object suitable for Stripe dispute submission |
| AC5 | Admin order detail page shows full event timeline using getOrderTimeline() |

Technical Notes

- OrderEvent has no update or delete operations — append-only enforced in application code

- getEvidencePackage() is the function called when admin clicks 'Export to Stripe portal'

Definition of Done

- Unit test: logOrderEvent called twice creates two separate records, neither overwrites the other

- getEvidencePackage returns all required fields for a test order with shipped status

EP-07 · Admin Dashboard & Monitoring 28 story points · 4 stories · Sprint 5

Platform admin panel: approval queues, order list, SLA flags, basic dispute visibility, PlatformSettings editor.

US-07-01 Admin order list with SLA flag indicators

| Points | Priority | Status | Epic | Sprint |
| --- | --- | --- | --- | --- |
| 5 pts | High | Todo | EP-07 Admin Dashboard | Sprint 5 |

As a platform admin, I want to to see all orders with real-time SLA status flags so I can immediately identify orders needing intervention so that no order falls through the cracks due to a non-responsive roaster

Dependencies: US-05-01  ·  US-01-03

Acceptance Criteria

| # | Acceptance Criteria |
| --- | --- |
| AC1 | Order list at admin.joeperks.com/orders shows all orders sorted by created_at desc, paginated 50/page |
| AC2 | Each row: order number, campaign/org name, roaster name, status badge, payout status, created date, SLA indicator |
| AC3 | SLA indicator: green (on track), amber (within 6h of breach), red (breached), grey (shipped/delivered) |
| AC4 | Clicking a row opens order detail with: all order fields, full event timeline, dispute record if exists, payout breakdown, and action buttons |
| AC5 | Action buttons: Mark Delivered, Contact Roaster (opens email compose), Issue Refund (with confirmation modal), Mark as Flagged |
| AC6 | Filter bar: filter by status, roaster, org, date range |
| AC7 | SLA summary at top of page: Critical (N) / Warning (N) / On Track (N) metric cards |
| AC8 | Admin can manually trigger payout from order detail (for edge cases) — requires confirmation |

Technical Notes

- SLA calculation: if status=CONFIRMED and now > fulfill_by — 6h = amber; now > fulfill_by = red

- Issue Refund: calls stripe.refunds.create(), updates Order.status = REFUNDED, logs OrderEvent ORDER_REFUNDED

Definition of Done

- Test order with 48h+ without shipping shows red SLA indicator

- Filter by roaster returns only that roaster's orders

- Manual deliver marks order correctly with OrderEvent

US-07-02 PlatformSettings editor in admin

| Points | Priority | Status | Epic | Sprint |
| --- | --- | --- | --- | --- |
| 5 pts | Medium | Todo | EP-07 Admin Dashboard | Sprint 5 |

As a platform admin, I want to to edit all platform business rules (fee percentages, SLA hours, payout hold days) from an admin UI without touching code so that I can tune business rules in response to real-world feedback without requiring a deployment

Dependencies: US-01-02  ·  US-01-03

Acceptance Criteria

| # | Acceptance Criteria |
| --- | --- |
| AC1 | Settings page at admin.joeperks.com/settings shows all PlatformSettings fields as editable inputs |
| AC2 | Fields: platform_fee_pct (%), platform_fee_floor ($), org_pct_min (%), org_pct_max (%), org_pct_default (%), sla_warn_hours, sla_breach_hours, sla_critical_hours, sla_auto_refund_hours, payout_hold_days, dispute_fee_cents ($), min_retail_spread_pct (%) |
| AC3 | Each field has a label, current value, and a brief description of what it controls |
| AC4 | Save button updates PlatformSettings singleton — confirmation modal: 'This will affect all future orders. Are you sure?' |
| AC5 | Changes take effect immediately — no restart required |
| AC6 | All inputs have validation: fee percentages 0–50%, hours 1–240, hold days 0–30 |

Technical Notes

- Settings are read at request time — no caching, always fresh from DB

- Consider adding ApplicationEvent log for settings changes: who changed what, when

Definition of Done

- Changing platform_fee_pct to 6% and creating a test order uses 6% in split calculation

- Invalid values rejected with clear error messages

US-07-03 Basic metrics dashboard for admin

| Points | Priority | Status | Epic | Sprint |
| --- | --- | --- | --- | --- |
| 5 pts | Medium | Todo | EP-07 Admin Dashboard | Sprint 5 |

As a platform admin, I want to to see key platform metrics at a glance: orders today, GMV, pending payouts, and active campaigns so that I have immediate visibility into platform health without running manual DB queries

Dependencies: US-05-01  ·  US-07-01

Acceptance Criteria

| # | Acceptance Criteria |
| --- | --- |
| AC1 | Admin home page at admin.joeperks.com shows metric cards: Orders Today, GMV This Month, Platform Revenue This Month, Active Campaigns, Roasters Active, Pending Payouts ($), Open Disputes |
| AC2 | Live order event feed shows the last 20 OrderEvents across all orders with: timestamp, event type, order number, actor |
| AC3 | Metrics calculated server-side on page load — no client-side fetching for initial render |
| AC4 | All metric counts are clickable links to the filtered order/dispute list |
| AC5 | Page auto-refreshes every 60 seconds or on manual refresh button |

Technical Notes

- GMV = SUM(gross_amount) for orders created in current month with status != CANCELLED

- Platform revenue = SUM(platform_amount) for orders with payout_status = TRANSFERRED

Definition of Done

- All 7 metric cards populated correctly from test data

- Event feed shows correct events in chronological order

US-07-04 Admin can manage roaster and org accounts: suspend, reactivate

| Points | Priority | Status | Epic | Sprint |
| --- | --- | --- | --- | --- |
| 3 pts | Low | Todo | EP-07 Admin Dashboard | Sprint 5 |

As a platform admin, I want to to suspend or reactivate any roaster or org account with an audit note so that I can remove bad actors from the platform without deleting their historical data

Dependencies: US-07-01

Acceptance Criteria

| # | Acceptance Criteria |
| --- | --- |
| AC1 | Roaster detail page at admin.joeperks.com/roasters/[id] shows all profile info, status, order history, debt balance |
| AC2 | Suspend button: prompts for reason (required), sets Roaster.status = SUSPENDED, logs ApplicationEvent, notifies roaster by email |
| AC3 | Reactivate button: sets Roaster.status = ACTIVE, logs ApplicationEvent |
| AC4 | Suspended roasters cannot receive new orders — storefront product availability check blocks them |
| AC5 | Same pattern for Org accounts at admin.joeperks.com/orgs/[id] |

Technical Notes

- Suspension does not cancel existing confirmed orders — those still process to completion

Definition of Done

- Suspending a roaster shows their products as unavailable on all storefronts

- Reactivation restores availability

EP-08 · Transactional Email System 22 story points · 6 stories · Sprint 3–4

All transactional emails: order confirm, shipped, delivered, impact message, SLA nudges, approval notifications using React Email + Resend.

US-08-01 Order confirmation email to buyer

| Points | Priority | Status | Epic | Sprint |
| --- | --- | --- | --- | --- |
| 3 pts | High | Todo | EP-08 Email System | Sprint 3 |

As a buyer, I want to to receive an order confirmation email immediately after payment so that I have a record of my purchase and know my order is being processed

Dependencies: US-01-04  ·  US-05-01

Acceptance Criteria

| # | Acceptance Criteria |
| --- | --- |
| AC1 | Email sent within 30 seconds of payment_intent.succeeded webhook processing |
| AC2 | Email contains: order number, org name and campaign description, items ordered with quantities and prices, fundraiser impact ('Your order will raise $X for [Org]'), shipping address, estimated delivery (from roaster's shipping rate label), support email |
| AC3 | Subject: 'Order confirmed — [Org Name] fundraiser #[JP-00001]' |
| AC4 | Email renders correctly in Gmail, Apple Mail, and Outlook |
| AC5 | EmailLog record created preventing duplicate sends |

Technical Notes

- Use React Email with Joe Perks brand colors and org logo if available

Definition of Done

- Test order triggers confirmation email within 30s, renders correctly on mobile

US-08-02 Roaster magic link fulfillment notification email

| Points | Priority | Status | Epic | Sprint |
| --- | --- | --- | --- | --- |
| 3 pts | High | Todo | EP-08 Email System | Sprint 4 |

As a roaster, I want to to receive an email with full order details and a single prominent link to fulfill the order so that I can act on the order immediately without logging into any system

Dependencies: US-01-04  ·  US-05-01

Acceptance Criteria

| # | Acceptance Criteria |
| --- | --- |
| AC1 | Email sent immediately after order confirmation |
| AC2 | Contains: order number, items and quantities, full shipping address (name, address, city, state, zip), your payout amount ('Your earnings: $X.XX'), prominent 'Fulfill this order' button linking to magic link URL |
| AC3 | Magic link URL is the full roasters.joeperks.com/fulfill/[token] URL |
| AC4 | Subject: 'New order to fulfill — #[JP-00001] for [Org Name]' |
| AC5 | Footer: 'Can't fulfill? Reply to this email or visit [magic link] to flag an issue' |

Technical Notes

- Payout amount shown = roaster_amount + shipping_amount (roaster_total) — the total they'll receive

Definition of Done

- Email renders correctly, magic link in button is valid and resolves to correct order

US-08-03 Shipped notification email to buyer with tracking

| Points | Priority | Status | Epic | Sprint |
| --- | --- | --- | --- | --- |
| 3 pts | High | Todo | EP-08 Email System | Sprint 4 |

As a buyer, I want to to receive an email when my coffee has shipped with tracking information so that I can track my package and know when to expect delivery

Dependencies: US-01-04  ·  US-05-02

Acceptance Criteria

| # | Acceptance Criteria |
| --- | --- |
| AC1 | Email sent immediately when roaster marks order as shipped |
| AC2 | Contains: order number, items shipped, tracking number, carrier name, direct tracking URL (e.g. ups.com/track?tracknum=...) |
| AC3 | Fundraiser reminder: 'Your purchase is raising $X for [Org Name]' |
| AC4 | Subject: 'Your coffee is on the way — [carrier] tracking [number]' |
| AC5 | Tracking URL generated correctly per carrier: UPS, FedEx, USPS, DHL — fallback to carrier website for 'Other' |

Technical Notes

- Carrier tracking URL map maintained in packages/email/tracking-urls.ts

Definition of Done

- Tracking URL for UPS test number resolves to correct UPS tracking page

US-08-04 Delivery confirmation + impact email to buyer

| Points | Priority | Status | Epic | Sprint |
| --- | --- | --- | --- | --- |
| 3 pts | High | Todo | EP-08 Email System | Sprint 4 |

As a buyer, I want to to receive an email when my order is delivered confirming how much I raised for the cause so that I feel the positive impact of my purchase and am more likely to purchase again

Dependencies: US-01-04  ·  US-05-03

Acceptance Criteria

| # | Acceptance Criteria |
| --- | --- |
| AC1 | Email sent when Order.status changes to DELIVERED |
| AC2 | Large impact statement: 'Your order raised $X.XX for [Org Name]!' |
| AC3 | Running total: 'The [Org Name] campaign has raised $Y total so far' |
| AC4 | Coffee prompt: 'Enjoy your coffee — and consider sharing the campaign with friends who love coffee too' |
| AC5 | Campaign share link included: joeperks.com/[slug] |
| AC6 | Subject: 'Your coffee arrived — and you raised $X.XX for [Org Name]!' |

Technical Notes

- total_raised on Campaign is the source for running total — update this when order is paid out, not delivered

Definition of Done

- Impact amount matches org_amount on Order. Campaign share link is correct and active

US-08-05 SLA warning and breach notification emails

| Points | Priority | Status | Epic | Sprint |
| --- | --- | --- | --- | --- |
| 3 pts | Medium | Todo | EP-08 Email System | Sprint 4 |

As a roaster and admin, I want to to receive escalating email notifications when an order is approaching or has breached its fulfillment SLA so that late orders are surfaced before buyers notice and have time to be resolved

Dependencies: US-01-04  ·  US-01-06  ·  US-05-01

Acceptance Criteria

| # | Acceptance Criteria |
| --- | --- |
| AC1 | T+24h (sla_warn_hours): roaster receives reminder email 'You have an order due tomorrow — [magic link to fulfill]' |
| AC2 | T+48h (sla_breach_hours): roaster receives urgent email 'URGENT: Order #JP-XXXXX is overdue'. Admin receives SLA breach alert with order details and direct link to admin order page |
| AC3 | T+72h (sla_critical_hours): admin receives critical alert 'Order #JP-XXXXX requires immediate intervention — 24h until auto-refund' |
| AC4 | T+96h (sla_auto_refund_hours): system auto-refunds buyer via stripe.refunds.create(), Order.status = REFUNDED, OrderEvent SLA_AUTO_REFUNDED created, admin notified of auto-refund, roaster notified with explanation |
| AC5 | All SLA emails use EmailLog deduplication — each (order_id, template) combination sent at most once |
| AC6 | Inngest sla-check job: queries ORDER WHERE status=CONFIRMED AND fulfill_by <= now() + 6h, processes each tier |

Technical Notes

- sla-check job stub from US-01-06 gets full implementation here

- Auto-refund does NOT recover Stripe processing fee from roaster at this stage — that's handled by RoasterDebt in Phase 2 SLA cost recovery

Definition of Done

- Test order with fulfill_by in the past: correct emails sent per tier

- auto-refund at T+96h creates Stripe refund in test mode

- EmailLog prevents duplicate SLA emails for same order

US-08-06 Application received and approval/rejection notification emails

| Points | Priority | Status | Epic | Sprint |
| --- | --- | --- | --- | --- |
| 2 pts | High | Todo | EP-08 Email System | Sprint 2 |

As a roaster or org applicant, I want to to receive email notifications at each stage of my application review so that I'm kept informed and don't need to chase the platform for updates

Dependencies: US-01-04

Acceptance Criteria

| # | Acceptance Criteria |
| --- | --- |
| AC1 | Roaster application received: sent on submit, contains: 'We received your application — review takes 3–5 business days' |
| AC2 | Roaster approved: sent on admin approval, contains: Stripe onboarding link and instructions to complete product setup |
| AC3 | Roaster rejected: sent on admin rejection, contains: reason provided by admin |
| AC4 | Org application received: sent on submit, contains: expected review process timeline |
| AC5 | Org pending roaster approval: sent when platform approves and routes to roaster, contains: 'Your application is with [Roaster Name] for approval — we'll update you soon' |
| AC6 | Org approved: sent after roaster + final admin approval, contains: link to org portal onboarding |
| AC7 | Org rejected: sent with reason |
| AC8 | All emails use EmailLog deduplication — each (entity_id, template) combination sent at most once |

Technical Notes

- Six distinct email templates, all in packages/email/templates/

- Template names: roaster_application_received, roaster_approved, roaster_rejected, org_application_received, org_pending_roaster_approval, org_approved, org_rejected

Definition of Done

- All 7 templates render correctly in React Email dev server and send successfully in test